## Main
Test Cases for Project
|  | Project Name | Anaar RMS Testing
|  | Created By | -
|  | Created Date | 2024-10-31
|  | Peer Review By | -
|  | Peer Reviewed Date | -
Module Name | Test Scenario ID | Test Scenario Description | TCs | Linked Document | Executed QA Name | Misc (Comments)
User Management | Login_Scen_1 | Validate login functionality by verifying successful login, handling invalid email/password entries, empty credentials, and database connection errors. | 5 | - | - | -
| Logout_Scen_2 | Verify that the Logout button functions correctly by successfully logging out the user and ensuring that the user session is terminated without errors. | 3
| App_Setting_Scen_3 | Verify the App Settings page displays correctly with functional Show Entries, Search Bar, Pagination, and Table Sorting. | 9
| AutoLogout_Scen_1 | Verify the system automatically logs out the user after a period of inactivity. | 1
Dashboard Management | Access_Scen_1 | Dashboard Access after Login | 2
| Sidebar_Scen_2 | Sidebar Navigation | 2
| Dashboard_Matrics_Scen_3 | Dashboard Metrics Display | 2
| Graph_Scen_4 | Graphs Display | 3
Branch Management | RANCH_ADD_SCEN_1 | Verify creation, listing and search of branches. | 3
| BRANCH_UPDATE_SCEN_2 | Verify branch creation, including success and error cases. | 2
| BRANCH_MISC_SCEN_3 | Verify branch deletion, search accuracy, and entry count display with error handling for assigned branches. | 5
Rider Management | RIDER_INFO_01 | Verify navigation to "Rider Info" tab from side bar | 17
| RIDER_ATTENDANCE_01 | Verify navigation to "Rider Attendance" tab | 14
Order Management | ADD_ORD_SCEN_1 | Verify navigation to Add Order page, validate input fields, and ensure correct branch auto-selection and manual change. | 19
| ORD_LIST_SCEN_2 | Validate Order List Page Functionalities | 11
| ORD_RATING_SCEN_3 | Validate Order rating Page Functionalities | 4
Product Management | PROD_SCEN_01 | Product Page Functionality | 16
| PROD_SCEN_02 | Category page functionalities | 11
Report Management | Order_Report_SCEN_2 | Verify Delivery Time Report and other functionalities of order report module. | 6
| Rider_Report_Scen_2 | Verify rider report page functionlities and display of data. | 1
136

## User
Scenario TID | Test Scenario | Test Case ID | Test Case Description | Preconditions | Test Data | Test Steps | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
Login_Scen_1 | Validate login functionality by verifying successful login, handling invalid email/password entries, empty credentials, and database connection errors. | TC-UM-001 | Verify user can log in with valid credentials. | User has valid credentials. | Email: admin@example.com Password: validpassword | 1. Navigate to the login page. 2. Enter valid email and password. 3. Click "Login." | User is redirected to the dashboard. | User is redirected to the dashboard. | Pass |  | Hi "user" should be displayed on dashboard | High | No
|  | TC-UM-002 | Verify user cannot log in with an invalid email. | User has an account with a valid email. | Email: invalid@example.com Password: validpassword | 1. Navigate to the login page. 2. Enter invalid email and valid password. 3. Click "Login." | Error message "Invalid email address" is displayed. | Error message "Invalid email address" is displayed. | Pass |  | - | High | No
|  | TC-UM-003 | Verify user cannot log in with an invalid password. | User has valid credentials. | Email: admin@example.com Password: invalidpassword | 1. Navigate to the login page. 2. Enter valid email and invalid password. 3. Click "Login." | Error message "Invalid password" is displayed. | Error message "Password Mismatch" is displayed. | Pass |  | Password Invalid would be an appropriate message | High | No
|  | TC-UM-004 | Verify user cannot log in with empty fields. | N/A | Email: <empty> Password: <empty> | 1. Navigate to the login page. 2. Leave email and password fields empty. 3. Click "Login." | Error message "Email and password required" is displayed. | User is unable to login and "Please fill out this field" appears | Pass |  | It should prompt for "email" and "password" if either field is left empty. | High | No
|  | TC-UM-005 | Verify appropriate message if there's no database access. | Simulate database disconnection. | Email: admin@example.com Password: validpassword | 1. Navigate to the login page. 2. Enter valid credentials. 3. Click "Login." | Error message "Unable to connect to the database" is displayed. |  | Not Executed |  |  | Critical | No
Logout_Scen_2 | Verify that the Logout button functions correctly by successfully logging out the user and ensuring that the user session is terminated without errors. | TC-UM-006 | Verify user can log out successfully. | User is logged into the dashboard. | N/A | 1. Click on the "Logout" button in the sidebar. | User is redirected to the login page. Toast message "Logout successful" is displayed. | User is redirected to the login page. | Pass |  | Toast message "Logout successful" may be displayed. | High | No
|  | TC-UM-007 | Verify clicking logout button logs the user out. | User is logged into the dashboard. | N/A | 1. Click on the "Logout" button. | User is logged out and redirected to the login page. | User is logged out and redirected to the login page. | Pass |  | - | High | No
|  | TC-UM-008 | Verify behavior if logout does not occur. | User is logged into the dashboard. | N/A | 1. Simulate logout failure (e.g., by altering logout function). 2. Click on "Logout." | User remains logged in. Error message "Logout failed" is displayed. | - | Not Executed |  |  | Critical | No
App_Setting_Scen_3 | Verify the App Settings page displays correctly with functional Show Entries, Search Bar, Pagination, and Table Sorting. | TC-UM-009 | Verify App Settings page displays correctly. | User is logged into the dashboard. | N/A | 1. Click on the "App Settings" button in the sidebar. | App Settings page is displayed with all controls and settings. | App Settings page is displayed with all controls and settings. | Pass |  |  | High | No
|  | TC-UM-010 | Verify "Show Entries" dropdown works correctly. | User is on App Settings page. | N/A | 1. Click on "Show Entries" dropdown. 2. Select different entries (e.g., 5, 10, 25). | Table updates to display the correct number of entries based on the selection. | Table updates to display the correct number of entries based on the selection. | Pass |  |  | Medium | No
|  | TC-UM-011 | Verify search bar filters results correctly. | User is on App Settings page. | Search Term: "delivery" | 1. Enter "delivery" into the search bar. 2. Press Enter or click search icon. | Results are filtered to show only entries containing the term "delivery." | Results are filtered to show only entries containing the term "delivery." | Pass |  |  | Medium | No
|  | TC-UM-012 | Verify pagination buttons work correctly. | User is on App Settings page. | N/A | 1. Check for multiple entries on the page. 2. Click on "Next" and "Previous" buttons. | Entries change correctly as per the pagination, displaying the expected results. | Entries change correctly as per the pagination, displaying the expected results. | Pass |  |  | Medium | No
|  | TC-UM-013 | Verify sorting functionality for the table. | User is on App Settings page. | N/A | 1. Click on sort arrow for each column (ID, Label, Value). | Table sorts correctly based on ascending/descending order. | Table sorts correctly based on ascending/descending order but doesnt restrict to current page entries/ | Fail |  |  | Medium | No
|  | TC-UM-014 | Verify that the "Edit" button is visible for each row in the App Settings table. | User is logged into the dashboard and on the App Settings page. | N/A | 1. Navigate to the App Settings page. 2. Look for the "Edit" button in front of each row. | Each row in the table has a visible "Edit" button in the "Action" column. | Each row in the table has a visible "Edit" button in the "Action" column. | Pass |  |  | High | No
|  | TC-UM-015 | Verify clicking the "Edit" button redirects to the correct edit screen. | User is on the App Settings page. | N/A | 1. Click on the "Edit" button in front of any row. | User is redirected to the edit screen with pre-filled data for the selected row. | User is redirected to the edit screen with pre-filled data for the selected row. | Pass |  |  | High | No
|  | TC-UM-017 | Verify the "Edit" button functions correctly after editing a row. | User is on the edit page after clicking "Edit" button. | N/A | 1. Edit the fields in the form. 2. Save the changes. 3. Navigate back to the App Settings page. | The edited row is updated with the new data. The "Edit" button reflects the changes. | The edited row is updated with the new data. The "Edit" button reflects the changes. | Pass |  |  | High | No
|  | TC-UM-018 | Verify the clicking "save" button in edit screen is dim when no changes are made in entries. | User is on the App Settings page with edit screen opened. | N/A | 1. Refresh the App Settings page. 2. Click on edit button. 3. Click save button without making any chnages. | User should be unable to save when no chnages are made and forced to click close button | Save button works fine even when no chnages are made and shows success toast message. | Fail |  |  | Medium | No
AutoLogout_Scen_1 | Verify the system automatically logs out the user after a period of inactivity. | TC-UM-019 | Validate that the application logs out the user if the session is idle for a specific timeout duration. | User is logged into the application. | N/A | 1. Log into the application. 2. Leave the session idle for the specified timeout duration (e.g., 15 minutes). 3. Observe the behavior. | The user session is terminated, and the user is redirected to the login page with a message such as "Session timed out." | The user session is terminated, and the user is redirected to the login page with a message such as "Session timed out." | Pass |  |  | High | No

## Dashboard
Scenario TID | Test Scenario | Test Case ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
Access_Scen_1 | Dashboard Access after Login | TC-DM-001 | Verify user can log in and access the dashboard. | User must have valid credentials. | 1. Enter valid username and password. 2. Click "Login." | Valid User Credentials | User is redirected to the dashboard. Toast message "Login successful" is displayed. | User is redirected to the dashboard. | Pass |  | Toast message "Login successful" may be displayed. | High | No
|  | TC-DM-002 | Verify user cannot log in with invalid credentials. | User must have invalid credentials. | 1. Enter invalid username and/or password. 2. Click "Login." | Invalid User Credentials | User remains on the login page. Error message "Invalid credentials" is displayed. | User remains on the login page. Error message is displayed. | Pass |  |  | High | No
Sidebar_Scen_2 | Sidebar Navigation | TC-DM-003 | Verify clicking "Rider" opens rider-related sections. | User is logged into the dashboard. | 1. Click on the "Rider" section in the sidebar. | Click on "Rider" | Rider information and attendance details are displayed correctly. | User directed to concerned section. However, "rider attendance" module also shows as primary in nav bar | Fail |  |  | High | No
|  | TC-DM-004 | Verify clicking "Order" opens order-related sections. | User is logged into the dashboard. | 1. Click on the "Order" section in the sidebar. | Click on "Order" | Order-related metrics and functionalities are displayed correctly. | Order-related metrics and functionalities are displayed correctly. | Pass |  |  | High | No
Dashboard_Matrics_Scen_3 | Dashboard Metrics Display | TC-DM-005 | Verify key metrics are displayed correctly on the dashboard. | User is logged into the dashboard. | 1. View the dashboard metrics. 2. Verify values for Total Branches, Total Orders Delivered, etc. | N/A | All metrics display accurate values reflecting the current system state. | Few metrics display wrong values | Fail |  | Probably tabs under development | High | No
|  | TC-DM-006 | Verify navigation to relevant sections when clicking on each dashboard tab | User is logged into the dashboard. | 1. Click on the "Active Riders" tab. 2. Click on the "Idle Riders" tab. 3. Click on the "Offline Riders" tab. 4. Click on the "Average Order Value" tab. 5. Click on the "Average Items Per Order" tab. 6. Click on the "Average Preparation Time" tab. 7. Click on the "Average Delivery Time" tab. 8. Click on the "Average Journey Time" tab. | Active Riders, Idle Riders, Offline Riders, Average Order Value, Average Items Per Order, Average Preparation Time, Average Delivery Time, Average Journey Time. | Each tab redirects the user to its relevant section/module with the corresponding data displayed. Example: Clicking "Active Riders" should show the section related to active riders, and so on for other tabs. | Sections/modules display relevant data according to the tab selected. | Fail |  |  | High | No
Graph_Scen_4 | Graphs Display | TC-DM-007 | Verify all graphs are displayed correctly on the dashboard. | User is logged into the dashboard. | 1. View the graphs section on the dashboard. | N/A | All graphs display without error, with accurate data visualizations. | Few graphs not showing correct data. | Fail |  |  | High | No
|  | TC-DM-008 | Verify download functionality for graphs works. | User is logged into the dashboard. | 1. Click on "Orders in a day" graph. 2. Select "Download PNG." 3. Save the file. | Select "Orders in a day" | Graph is downloaded successfully in the selected format. | Graph is downloaded successfully in the selected format. | Pass |  |  | Medium | No
|  | TC-DM-09 | Verify handling of graphs with no data. | User is logged into the dashboard. | 1. Simulate a state where graph data is empty. 2. Refresh the dashboard. | Graph with No Data | Graph displays message "No data available" without any error. | Graph doesnt show any data. | Pass |  | "No data available" should be displayed. | Medium | No

## Branch
Scenario TID | Test Scenario | Test Case ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
BRANCH_ADD_SCEN_1 | Verify branch creation, including success and error cases. | BRANCH_ADD_01 | Verify that admin is able to create a new branch | Admin is logged in. | 1. Click on "Branches" in nav bar and open branch list 2. Click on add new. 3. Enter all the required details in add vendor screen 4. click save | "Branch Name: ""Ravi Branch"" Required fields filled" | New branch is created with a unique ID. Data is verified. Success toast message is displayed. | New branch is created even with wrong data and no validations | Fail |  |  | High
|  | BRANCH_ADD_02 | Verify that error messages are displayed for missing fields | Admin is logged in. | 1. Click on "Add New Branch." 2. Leave required fields empty. 3. Click "Save." | Required fields left empty | Error messages indicate which fields are required. | Error messages indicate which fields are required. But with few empty fields even it creates the branch | Fail |  | The form should require all mandatory fields and visually indicate them (e.g., with an asterisk), which isn't happening in this scenario. | High
|  | BRANCH_ADD_03 | Verify that duplicate branch names cannot be created | Admin is logged in. | 1. Click on "Add New Branch." 2. Fill in fields with an existing branch name. 3. Click "Save." | "Branch Name: ""Duplicate Branch"" Existing Name: ""Existing Branch""" | Error message indicates the branch name already exists. | An integrity constraint violation occurs, and the system throws an SQL error due to the duplicate email. | Fail |  |  | High
BRANCH_UPDATE_SCEN_2 | Verify updating an existing branch and its visibility. | BRANCH_UPDATE_01 | Verify that admin can update an existing branch | Admin is logged in. Branch exists. | 1. Select the branch. 2. Click "Edit." 3. Modify required fields. 4. Click "Save." | "Branch Name: ""Existing Branch"" Updated Name: ""Updated Branch""" | Branch is updated. Data is verified. Success toast message is displayed. | Branch is updated. Data is verified. Success toast message is displayed. | Pass |  |  | High
|  | BRANCH_UPDATE_02 | Verify that admin can change the visibility of a branch | Admin is logged in. Branch exists. | 1. Select the branch. 2. Click on "Open/Close." | Branch Name: "Branch to Toggle" | Branch visibility is changed. Status is updated accordingly. | Branch visibility is changed. Status is updated accordingly. | Pass |  |  | Medium
BRANCH_MISC_SCEN_3 | Verify branch deletion, search accuracy, and entry count display with error handling for assigned branches. | BRANCH_DELETE_01 | Verify that admin is able to delete a branch. | Admin is logged in. Branch exists. | 1. Select the branch from the list. 2. Click "Delete". 3. Confirm deletion when prompted. 4. Observe the response. 5. Refresh the page and check if the branch is removed. | Branch Name: "Branch to Delete" | The branch should be deleted successfully, and a confirmation toast message should be displayed, along with the updated branch list. | Error 404 page is displayed immediately after deletion, but the branch is successfully deleted upon refreshing the page. | Fail |  |  | High
|  | BRANCH_DELETE_02 | Verify confirmation prompt before branch deletion | Ensure that before a branch is deleted, the system asks for a confirmation to prevent accidental deletions. | Admin is logged in and a branch exists. | 1. Log in as Admin and go to branch list from Nav Bar. 2. Select the branch to delete. 3. Click the "Delete" button. 4. Verify the confirmation prompt appears asking to confirm the deletion. 5. Confirm deletion. | The system should display a confirmation prompt asking for deletion confirmation before performing the action. | The confirmation prompt doesn't appears before deletion. | Fail |  |  | High
|  | BRANCH_SEARCH_01 | Verify that search functionality works correctly | Admin is logged in. | 1. Go to Branch list from Nav Bar 2. Type a branch name in the search bar. | Search Term: "Test Branch" | Relevant branches are displayed. Incorrect input shows "No branch matches." | Relevant branches are displayed. Incorrect input shows "No branch matches." | Pass |  |  | Medium
|  | BRANCH_SHOW_ENTRIES_01 | Verify that show entries functionality works correctly | Admin is logged in. | 1. Go to Branch list from Nav Bar 2. Click on entries dropdown | Entries Dropdown Value: "10" | Number of entries displayed matches the selection. | Number of entries displayed matches the selection. | Blocked |  |  | Medium
|  | BRANCH_LIST_SCEN_1 | Verify sorting functionality of branch table columns | Verify that clicking on the sort arrows for the table columns works correctly. | 1. Log in as Admin. 2. Click on "Branches" in the navigation bar. 3. Verify the table displays with columns: "ID", "Info", "Time", "Open/Close", "Action". 4. Click the sort arrows for each column ("ID", "Info", "Time"). 5. Verify if the table sorts the data in ascending and descending order for each column. | The table should correctly sort the data based on the column clicked (ascending and descending order). | The table sorts correctly for all columns (ID, Info, Time, etc.) when the sort arrows are clicked. | The table sorts correctly for all columns (ID, Info, Time, etc.) when the sort arrows are clicked. | Pass |  |  | High
|  | BRANCH_ASSIGNMENT_01 | Verify behavior when trying to delete a branch assigned to an order | Admin is logged in. Branch is assigned. | 1. Select the branch. 2. Click "Delete." 3. Confirm deletion. | Branch Name: "Assigned Branch" | Error message indicates branch cannot be deleted as it is assigned to an order. |  | Not Executed |  |  | High

## Rider
Scenario TID | Test Scenario | Test Case ID | Test Case Title | Pre Condition | Steps to Execute | Test Data | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority
RIDER_INFO_01 | Verify navigation to "Rider Info" tab from side bar | RIDER_INFO_01 | User successfully directed to Rider Info page when clicked on the tab | User is logged in. | 1. Click on "Rider Info" tab in the nav bar. | N/A | Rider Info page loads with "Add New" and "Track" options displayed. | Rider Info page loads with "Add New" and "Track" options displayed. | Pass |  |  | High
|  | RIDER_INFO_02 | New rider pop-up opens, and rider is added successfully after entering data | User is on "Rider Info" page. | 1. Click "Add New" button. 2. Fill in the necessary details and click "Add." | Name: "John Doe" Email: "john@doe.com" Phone: "03000000001" Password: "password" | Rider is added to the list, success message displayed. | Rider is added to the list, success message displayed. | Pass |  |  | High
|  | RIDER_INFO_03 | Rider receives login credentials via email. | New rider created on the portal. | 1. Complete the rider creation process. 2. Check email for login credentials. | Rider Name: "John Doe" Email: "john@doe.com" | Rider receives login credentials via email. | No email received. | Fail |  | Email notification issue needs to be resolved. | High
|  | RIDER_INFO_04 | Adding a new rider shows correct data on screen, and an ID is assigned. | User is on "Rider Info" page. | 1. Add a new rider by filling in all details and clicking "Add." | Name: "Jane Smith" Email: "jane@smith.com" Phone: "03111111111" Password: "password123" | Rider data should be displayed correctly, and ID should be assigned. | ID is not being assigned; however, data is correct. | Fail |  | Fix the ID assignment process. | High
|  | RIDER_INFO_05 | Validation of all fields: Name, Email, Phone number, Password, etc. | User is on "Rider Info" page. | 1. Enter invalid or missing data in each field (name, email, phone, password, etc.) and click "Add." 2. Observe error messages for each field. | Name: "" Email: "invalidemail" Phone: "12345" Password: "" | Error messages should be displayed for invalid/empty fields (e.g., invalid email, phone format). | Validation of entries failed for email and phone. | Fail |  | Each entry should be validated for format and type/size. | High
|  | RIDER_INFO_06 | Duplicate entry validation (Phone number, Name) | User is on "Rider Info" page. | 1. Enter the same phone number or name as an existing rider and click "Add." | Name: "John Doe" Phone: "03000000001" | Error message should be displayed indicating duplicate entry (phone number or name already exists). | Accepting duplicate names; rest fine. | Fail |  | Names should also be unique like phone numbers. | High
|  | RIDER_INFO_07 | Verify success toast message after branch assignment or change. | User is on "Rider Info" page. | 1. Select a branch from the dropdown for the rider. 2. Click "Save" or "Assign." 3. Change the branch from the dropdown. Observe success message. | Branch: "Ravi Branch" New Branch: "New Branch" | Success message should be displayed after branch assignment or change. | Success message not displayed after branch assignment or change. | Fail |  |  | High
|  | RIDER_INFO_08 | Verify notification sent on mobile app after branch assignment or change. | User is on "Rider Info" page. | 1. Select a branch from the dropdown for the rider. 2. Click "Save" or "Assign." 3. Change the branch from the dropdown. Observe notifications. | Branch: "Ravi Branch" New Branch: "New Branch" | Notifications should be sent to the rider and the branch upon assignment or change. | No notification sent. | Fail |  | Check notification service integration. | High
|  | RIDER_INFO_09 | Amount collection done successfully, and toast notification appears. | User is on "Rider Info" page. | 1. Click "Collect Amount." 2. Verify if the toast message appears and the rider's wallet updates. | Rider: "John Doe" Amount: "500 PKR" | Amount should be collected successfully, and a toast message should appear. | Collection button not working; no toast message. | Fail |  |  | High
|  | RIDER_INFO_10 | Amount collection notification on app when clicking "Collect Amount" | Rider is logged in on the app. | 1. Click "Collect Amount" in the "Rider Info" page. | Rider: "Jane Smith" Amount: "1000 PKR" | Amount collection notification is sent to the rider app successfully. | Blocked due to backend issue. | Blocked |  |  | High
|  | RIDER_INFO_11 | Verify if rider info can be edited successfully, and toast message is shown on web and app. | User is on "Rider Info" page. | 1. Select a rider to edit. 2. Change necessary fields (name, email, etc.). 3. Click "Save." Observe updates and notifications. | Rider: "John Doe" New Name: "John Updated" New Email: "john.updated@doe.com" | Rider info should be updated successfully, and notifications should be sent. | Edit successful; no web toast or mobile notification. | Fail |  |  | High
|  | RIDER_INFO_12 | Verify if adding a rider on web and then logging with same credentials allows login on app. | New rider added on the web. | 1. Add a rider on the web. 2. Attempt to log in with the same credentials on the mobile app. | Name: "Jane Smith" Email: "jane@smith.com" Password: "password123" | Rider should be able to log in on the mobile app with the same credentials. | Works only with a rider added a few days back; not with newly created riders. | Fail |  |  | High
|  | RIDER_INFO_13 | Login with rider credentials on mobile app and check if correct data is shown. | Rider is created and logged in. | 1. Log in with valid rider credentials on the mobile app. 2. Verify displayed data. | Rider: "John Doe" Email: "john@doe.com" Password: "password" | Correct rider data should be shown on the mobile app. | Yes, data is displayed correctly. | Pass |  |  | Medium
|  | RIDER_INFO_14 | Verify toggle for online/offline works correctly and toast message appears. | Rider is logged in on the app. | 1. Toggle the rider's online/offline status. 2. Verify functionality and toast messages. | N/A | Toggle button should function correctly, and toast messages should appear. | Toggle works; toast is correct but functionality fails due to location detection issues. | Fail |  |  | High
|  | RIDER_INFO_15 | Verify sorting functionality for columns (ID, Info, Branch, Wallet, Order Cap). | User is on "Rider Info" page. | 1. Click sorting arrows for each column: ID, Info, Branch, Wallet, Order Cap. 2. Verify sorting order. | Columns: ID, Info, Branch, Wallet, Order Cap | The table should sort correctly by each column when the respective arrow is clicked. | The table sorts correctly by each column. | Pass |  |  | High
|  | RIDER_INFO_16 | Rider list navigates to next/previous page. | User is on "Rider Info" page. | 1. Click "Next" or "Previous" page buttons. | N/A | Rider list should navigate to the next or previous page without issues. | Navigation works correctly. | Pass |  |  | Low
|  | RIDER_INFO_17 | Verify that entries dropdown (10, 25, 50, 100) works correctly. | User is on "Rider Info" page. | 1. Select a value from the entries dropdown. 2. Verify if the displayed data adjusts to the selected number of entries per page. | Values: 10, 25, 50, 100 | The rider list should adjust to display the correct number of entries per page. | Works fine for all values. | Pass |  |  | Medium
RIDER_ATTENDANCE_02 | Verify functionality of "Rider Attendance" | RIDER_ATDC_01 | Access Rider Attendance Page | User logged in as Admin. | User logged in as Admin. | 1. Click "Rider Attendance" in side bar. | "Rider Attendance" page loads with table view. | "Rider Attendance" page loads. | Pass |  |  | High
|  | RIDER_ATDC_02 | Approve Attendance with Images | Click "Approve" action in attendance. | Rider submits attendance with 2 images. | 1. Click "Approve." | Attendance marked as approved, success message displayed. |  | Not Checked |  |  | High
|  | RIDER_ATDC_03 | Prevent Order Assignment for Unapproved Rider | Assign order to rider. | Rider attendance not approved. | 1. Attempt to assign order to rider. | Rider not assignable for order, warning message shown. |  | Not Checked |  |  | High
|  | RIDER_ATDC_04 | Approve Pending Rider Attendance | Approve rider attendance. | Rider attendance pending approval. | 1. Approve rider attendance. | Session start time/date updates, success message displayed. |  | Not Checked |  |  | Medium
|  | RIDER_ATDC_05 | Validate Two Images for Attendance | Attempt to submit attendance with 1 image. | Rider logging attendance. | 1. Submit attendance. | Error message prompts for missing second image. |  | Not Checked |  |  | Medium
|  | RIDER_ATDC_06 | View Uploaded Rider Attendance Images | Click "View" on attendance row. | Rider attendance submitted with images. | 1. Click "View" on attendance row. | Images uploaded by rider display in popup. |  | Not Checked |  |  | High
|  | RIDER_ATDC_07 | Sort Attendance Records by Session Times | Click sorting icons on start/end session columns. | Attendance records present. | 1. Click sorting icons. | Records sorted correctly based on session times. |  | Not Checked |  |  | Medium
|  | RIDER_ATDC_08 | Validate Images Required for Attendance | Try submitting without images. | Rider logs attendance. | 1. Attempt to submit attendance without images. | Error message prompts images required. |  | Not Checked |  |  | Medium
|  | RIDER_ATDC_09 | Approve Pending Attendance | Approve attendance. | Rider attendance awaiting approval. | 1. Click "Approve." | Success message confirms approval action. |  | Not Checked |  |  | Medium
|  | RIDER_ATDC_10 | End Rider Session | Admin clicks End Session. | Approved rider in active shift. | 1. Click "End Session." | End session time updates for rider, success message displayed. |  | Not Checked |  |  | Medium
|  | RIDER_ATDC_11 | Assign Order to Active Rider Only | Assign order to rider. | Rider attendance approved. | 1. Attempt to assign order. | Only active riders appear for assignment, inactive riders hidden. |  | Not Checked |  |  | High
|  | RIDER_ATDC_12 | Navigate Attendance Records Pages | Click next/previous page buttons. | Multiple attendance records. | 1. Click next/previous page buttons. | Table navigates between pages correctly. |  | Not Checked |  |  | Low
|  | RIDER_ATDC_13 | Search Attendance by Rider ID or Name | Search by rider ID or name. | Multiple attendance records. | 1. Enter rider ID/name in search. | Table filters to show relevant records. |  | Not Checked |  |  | Low
|  | RIDER_ATDC_14 | Rider Login with Invalid Credentials | Enter incorrect login credentials. | Rider login attempt. | 1. Enter incorrect credentials. | Error message prompts invalid login. |  | Not Checked |  |  | Medium

## Order
Scenario TID | Test Scenario | Test Case Id | Test Case Title | Pre Condition | Test Data | Steps to Execute | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
ADD_ORD_SCEN_1 | Verify navigation to Add Order page, validate input fields, and ensure correct branch auto-selection and manual change. | ADD_ORD_01 | Verify navigation to Add Order page | User logged into the system | None | 1. Click "Add Order" button. | User is navigated to the Add Order page with confirmation toast. | User is navigated to the Add Order page with confirmation toast. | Pass |  |  | High | No
|  | ADD_ORD_02 | Verify return to previous page on failure | User logged into the system | None | 1. Simulate a navigation failure (e.g., disconnect the database). 2. Attempt to navigate back to the previous page. | User should not be able to navigate to the previous page. An error message is displayed. | Not Checked | Not Checked |  |  | High | No
|  | ADD_ORD_03 | Verify empty fields submission behavior (Add Order Page) | User on Add Order page | Phone: ""; Name: "John"; Address: "456 Avenue" | 1. Leave required fields empty and submit the form. | Error message should prompt the user to fill all required fields. | No prompt shown. | Fail |  | UX error. | High | No
|  | ADD_ORD_04 | Verify valid input acceptance (Add Order Page) | User on Add Order page | Phone: "+923145643271"; Name: "Ali"; Address: "123 Street" | 1. Enter valid data into Phone, Name, and Address fields. 2. Submit the form. | The form should accept the valid inputs and ask for product selection. | Form accepts correct inputs. | Pass |  |  | High | No
|  | ADD_ORD_05 | Verify error message for invalid input (Add Order Page) | User on Add Order page | Phone: "1234"; Name: ""; Address: "" | 1. Enter invalid data for Phone, Name, and Address. 2. Submit the form. | Error messages should appear for each invalid field, notifying the user of the issue. | Errors shown successfully. But wrong error thrown for GPS address. | Fail |  |  | High | No
|  | ADD_ORD_06 | Verify validation error clears on correct input (Add Order Page) | User on Add Order page | Phone: "0341..."; Name: "Ali" | 1. Enter invalid data in the required fields. 2. Correct the errors and submit. | Validation errors should disappear after valid data is entered and the user moves to the next tab. | Validation error disappears only for number, not other fields. | Fail |  |  | High | No
|  | ADD_ORD_07 | Verify phone number field accepts common local formats (Add Order page) | User logged into the application | Phone number (e.g., 0341...) | 1. Navigate to the "Add Order" page. 2. Find the "Phone Number" field in the "Order Details" section. 3. Delete the pre-filled country code (+92). 4. Enter a local phone number (e.g., 0341...). 5. Observe the issue. | The phone number field should accept the local phone number format (e.g., 0341...) after removing the country code. | The system does not accept local phone number format. | Pass |  |  | High | No
|  | ADD_ORD_08 | Verify special character handling in Address (Add Order Page) | User on Add Order page | Address: "Invalid Address!" | 1. Enter special characters in the Address field. 2. Submit the form. | Error message should appear for invalid address input. | Validation failed. | Fail |  |  | High | No
|  | ADD_ORD_09 | Verify Branch auto-selection functionality (Add Order Page) | User logged in, location service enabled | None | 1. Navigate to Add Order page with location services enabled. | The correct branch should be auto-selected based on user location. | Blocked | Blocked |  |  | Medium | No
|  | ADD_ORD_10 | Verify manual branch selection functionality (Add Order Page) | User logged into the system | Branch options (e.g., Branch 1, Branch 2) | 1. Navigate to Add Order page. 2. Manually select a branch from the available options. | The selected branch should be displayed after selection. | Branch selected but only branches in range should appear. | Fail |  |  | High | No
|  | ADD_ORD_11 | Verify GPS Address field usability on Add Order page | User logged into the application | None | 1. Log in to the application. 2. Navigate to the "Add Order" page. 3. Observe the GPS Address field. 4. Try saving the order without filling in the GPS Address. | If mandatory, the GPS Address field should guide the user to select a location from the map interface. If optional, the field should be marked as "Optional." | GPS Address field lacks guidance or indication. | Pass |  | Issue noted about field usability | Medium | No
|  | ADD_ORD_12 | Verify product section updates on branch selection (Add Order Page) | User on Add Order page | Product: "Item A" | 1. Select a branch, then verify that the "Products" section updates with available items. | The product section should update dynamically based on the selected branch. | Blocked | Blocked |  |  | Medium | No
|  | ADD_ORD_13 | Verify navigation on "Add to Cart" button click (Add Order Page) | User on Add Order page | Product: "Item A" | 1. Click "Add to Cart" for any product on the page. | The "Add to Cart" button should open the cart and allow quantity adjustments. | The "Add to Cart" button opens the cart but is under development. | Fail |  |  | High | No
|  | ADD_ORD_14 | Verify complete product display in the "All Products" tab | User logged into the application | None | 1. Log in to the application. 2. Navigate to the "Add Order" page and go to the "Product List" section. 3. Search for products in the "All Products" tab. 4. Observe the products listed. | All products from various categories (e.g., drinks, sides, desserts) should be visible in the "All Products" tab. | Only one drink category product is shown. | Pass |  | Issue with product filtering | High | No
|  | ADD_ORD_15 | Verify correct behavior on selecting multiple items (Add Order Page) | User on Add Order page | Products: "Item A", "Item B" | 1. Select multiple products and click "Add to Cart". | The system should allow adding multiple items and show the updated cart. | The system allows adding multiple items and shows the updated cart. | Pass |  |  | Medium | No
|  | ADD_ORD_16 | Verify correct calculation of delivery charges | User logged into the application | Address and branch selection | 1. Log in to the application. 2. Navigate to the "Add Order" page. 3. Select an address and branch. 4. Observe the "Delivery Charges" field. | The "Delivery Charges" field should display the correct amount based on the selected address and branch. | "NaN" is displayed instead of a valid value. | Pass |  | Issue related to calculation error | High | No
|  | ADD_ORD_17 | Verify successful order submission (Add Order Page) | User on Add Order page | Phone: "0341..."; Product: "Item A"; Branch: "Branch 1" | 1. Complete the order form with all necessary details. 2. Submit the form. | The order should be submitted successfully, and the user should be directed to the active order screen. | The order be submitted successfully, and the user directed to the active order screen. | Pass |  |  | High | No
|  | ADD_ORD_18 | Validate Total Calculation | Products in cart, delivery fee applied. | Product prices, delivery fee | 1. Cross-check subtotal, delivery fee, and total amount in the cart. | Values reflect correct calculations; no error messages shown. | Correct calculations; no error messages shown. | Pass |  | Accurate calculations ensure pricing correctness. | High | No
|  | ADD_ORD_19 | Validate Total Calculation with discounts | Products in cart, delivery fee applied. | Product prices, delivery fee | 1. Apply discount to cart. | Total reflects discount applied correctly; error if total calculation fails. |  | Not Checked |  | Discounts tested to ensure customer benefit. | High | No
ORD_LIST_SCEN_2 | Validate Order List Page Functionalities | LIST_SCEN_01 | Verify "Date From" and "Date To" Tabs in Order List | Logged in as admin. | N/A | 1. Navigate to "Order List" page. 2. Hover over "Date From" and "Date To" tabs. | Tabs should display clear labels indicating functionality. | Tabs lack clear labels, confusing users. | Fail |  | UI/UX issue impacting usability. | Medium | No
|  | LIST_SCEN_02 | Validate date filter functionality | Logged in as admin. | Date range | 1. Use the date filter on "Order List". 2. Observe results. | Filter returns accurate order data based on the selected date range. | Filter does not return correct results. | Fail |  | Ensures date filter is accurate. | High | No
|  | LIST_SCEN_03 | Verify "Order Status" dropdown functionality | Logged in as admin. | N/A | 1. Open "Order Status" dropdown. | Dropdown should display available order statuses (e.g., "Accepted", "Picked", "Shipped"). | No statuses available in the dropdown. | Fail |  | Dropdown must show options for usability. | High | No
|  | LIST_SCEN_04 | Verify hover tooltips for action icons | Logged in as admin. | N/A | 1. Hover over action icons in the last column of the "Order List" page. | Correct tooltip text appears for each icon (e.g., "Edit Order", "View Order Details"). | All icons show incorrect tooltip "Order Detail". | Fail |  | UI issue causing confusion. | Medium | No
|  | LIST_SCEN_05 | Validate "Edit" button functionality . | Logged in as admin. | N/A | 1. Click "Edit" button for an order. | Redirection to "Add Order" page is immediate without delay. | Delays or failures observed for large orders. | Fail |  | Performance bottleneck identified. | High | No
|  | LIST_SCEN_06 | Verify "Home" link in breadcrumb navigates to home page | Logged in as admin. | N/A | 1. Click "Home" link in "Home/ Orders" breadcrumb. | Clicking "Home" redirects user to home page. | "Home" link does not redirect anywhere. | Fail |  | Breadcrumb functionality is broken. | Medium | No
|  | LIST_SCEN_07 | Verify Search Bar Functionality | User is logged in and on the Order List page in Manage Orders | Search term (e.g., "Order123") | 1. Navigate to the Manage Orders page. 2. Enter a search term in the search bar. 3. Press Enter or click the search icon. | The orders matching the search term should be displayed in the table. | Search results are as expected, only relevant orders are displayed. | Pass |  |  | High | No
|  | LIST_SCEN_08 | Verify Page Navigation (Next/Previous) | User is logged in and on the Order List page in Manage Orders | N/A | 1. Navigate to the Manage Orders page. 2. Click on the Next page button. 3. Click on the Previous page button. | The page should correctly display the next/previous set of orders, as per the pagination. | Page navigation works as expected. | Pass |  |  | High | No
|  | LIST_SCEN_09 | Verify Sorting Arrows Functionality | User is logged in and on the Order List page in Manage Orders | N/A | 1. Navigate to the Manage Orders page. 2. Click the sorting arrow for each column (ID, Name, etc.). | The table should sort the records based on the column selected, in ascending/descending order. | Sorting works as expected for each column. | Pass |  |  | High | No
|  | LIST_SCEN_10 | Verify "Show {} Entries" Button Functionality | User is logged in and on the Order List page in Manage Orders | N/A | 1. Navigate to the Manage Orders page. 2. Click the "Show {} Entries" dropdown. 3. Select a different number of entries (e.g., 10, 20, etc.). | The table should adjust to show the selected number of entries per page. | Table updates correctly based on the selected number of entries. | Pass |  |  | Medium | No
|  | LIST_SCEN_11 | Verify Changing Order Status Only Changes Status | User is logged in and on the Order List page in Manage Orders | Order with a status that can be changed (e.g., "Pending") | 1. Navigate to the Manage Orders page. 2. Change the status of an order to "Paid" from the status column. 3. Observe the behavior of the page after changing the status. | The order status should change to "Paid" without any redirection or page reload. | The page redirects to an unexpected or incorrect link after changing the order status. | Fail |  | This behavior is unusual and unexpected. | High | No
ORD_RATING_SCEN_3 | Validate Order rating Page Functionalities | ORD_RATING_01 | Verify search bar functionality on order rating page | User is logged into the dashboard and on the "Order Rating" page | N/A | 1. Navigate to the "Order Rating" page under "Manage Order". 2. Enter a search term in the search bar. 3. Press the "Search" button. | The search bar should filter and show results based on the search term entered. | The search bar is not filtering correctly or returning inaccurate results. | Fail |  |  | High | No
|  | ORD_RATING_02 | Verify pagination functionality on the order rating page | User is logged into the dashboard and on the "Order Rating" page | N/A | 1. Navigate to the "Order Rating" page under "Manage Order". 2. Click on "Next" and "Previous" buttons. | The page should navigate correctly to the next and previous pages with the correct order of entries. | Page navigation through "Next" and "Previous" works as expected. | Pass |  |  | Medium | No
|  | ORD_RATING_03 | Verify sorting functionality on the order rating page | User is logged into the dashboard and on the "Order Rating" page | N/A | 1. Navigate to the "Order Rating" page under "Manage Order". 2. Click on the sorting arrows for each column (ID, Order Number). | The sorting arrows should correctly sort the data in ascending and descending order for each column. | Sorting arrows are not functioning correctly for the ID and Order Number columns. | Fail |  |  | High | No
|  | ORD_RATING_04 | Verify functionality of the "Show {} Entries" button | User is logged into the dashboard and on the "Order Rating" page | N/A | 1. Navigate to the "Order Rating" page under "Manage Order". 2. Click the "Show {} Entries" button to select a different number of entries to display. | The "Show {} Entries" button should correctly update the number of entries displayed on the page. | The "Show {} Entries" button is working fine and updates the entries as expected. | Pass |  |  | Medium | No

## Product
Scenario TID | Test Scenario | Test Case Id | Test Case Title | Pre Condition | Steps to Execute | Test Data | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
PROD_SCEN_01 | Product Page Functionality | PROD_01 | Verify clicking on "Products" in the sidebar navigates to the "Products & Variations" page. | User is logged in as admin. | 1. Click on "Products" in the sidebar. | N/A | User is directed to "Products & Variations" page. | User is directed to "Products & Variations" page. | Pass |  |  | High
|  | PROD_02 | Verify "Choose Product" and "Add Product" sections have sorting and search bar functionalities. | On "Products & Variations" page. | 1. Use sorting to sort by ID. 2. Enter a product name in the search bar to filter results. | Product Name | Products list updates based on selected sorting option. Matching products displayed or "No results found" for non-matching entries. | Products list updates based on selected sorting option. Matching products displayed or "No results found" for non-matching entries. | Pass |  |  | Medium
|  | PROD_03 | Verify clicking "Add Product" displays a form popup with required product details. | On "Products & Variations" page. | 1. Click on "Add Product" button. | N/A | Popup displays fields for Category, Product Name, Price, Product Description, Image, Copy Variation, Price, with "Add" and "Close" buttons. | Pop up appears and adding entries is successful. | Pass |  |  | High
|  | PROD_04 | Verify adding a new product displays a success message and lists the product in "Choose Product". | On "Add Product" popup, required fields filled. | 1. Fill all fields in the popup and click "Add". | Category: Pizza, Product Name: Pan Pizza, Price: 500 | Success message "Product added successfully" displayed. New product appears in "Choose Product" list with correct ID, image, and name. | Success message "Product added successfully" displayed. New product appears in "Choose Product" list with correct ID, image, and name. | Pass |  |  | High
|  | PROD_05 | Verify error messages for required fields when adding a product without filling mandatory fields. | On "Add Product" popup. | 1. Click "Add" without entering any data. | N/A | Error messages under each required field (e.g., "Category is required", "Product Name is required"). | No error message appeared and pop up closed. | Fail |  |  | High
|  | PROD_06 | Verify the search functionality in "Choose Product" filters results accurately. | Products are added. | 1. Enter product name in the search bar. | Product Name: Fresh Juice | Products matching the search term appear in "Choose Product". If no match, display "No results found". | Matching product appears. | Pass |  |  | Medium
|  | PROD_07 | Verify "Show Entries" in "Products & Variations" works as per the selected value. | On "Products & Variations" page. | 1. Select different values (e.g., 10, 20) from "Show Entries" dropdown. | Entries per page: 10, 20 | Product list updates to display the selected number of entries per page. | Product list updates to display the selected number of entries per page. | Pass |  |  | Low
|  | PROD_08 | Verify sorting functionality for products by ID in "Choose Product". | On "Products & Variations" page. | 1. Sort products by ID in ascending and descending order. | Product ID, Product Name | Products are sorted in selected order, with correct data reflected in each entry. | Workd correctly but sort arrows for image shouldn't be there. | Fail |  |  | Medium
|  | PROD_09 | Verify error handling for duplicate product names. | On "Add Product" popup. | 1. Attempt to add a product with an existing name. | Product Name: Fresh Juice | Error message "Product name already exists" is displayed. Product is not added. | No error thrown and product added again. | Fail |  |  | High
|  | PROD_10 | Verify product images are uploaded successfully and displayed correctly in "Choose Product". | On "Add Product" popup. | 1. Upload a valid image file for the product. 2. Click "Add". | Image File: product_image.jpg | Product image is uploaded and displayed in "Choose Product" section. Success message "Product added successfully". | Product image is uploaded and displayed in "Choose Product" section. Success message "Product added successfully". | Pass |  |  | High
|  | PROD_11 | Verify validations for name and price tabs for correct format. | On "Add Product" popup. | 1. Enter wrong product name 2. Enter words in price tab | Nil | Error sould be thrown that wrong entries made. | No error thrown and accepts all kind of values. | Fail |  |  | High
|  | PROD_12 | Verify "Home/ Products & Variations" link in breadcrumb navigates to home page | On "Products & Variations" page. | 1. Click on "Products" in the sidebar. | N/A | Clicking Home link should take to home page. | Clicking Home page doesn't redirect to home page. | Fail |  |  | Medium
|  | PROD_13 | Verify deleting a product displays confirmation message and removes product from list. | Product exists in "Choose Product". | 1. Click "Delete" on a product in the list. 2. Confirm deletion. | Product ID: 1024 | Confirmation message "Are you sure?" appears. On confirm, product is deleted and success message "Product deleted" displays. Product removed from list. | Confirmation message "Are you sure?" appears. On confirm, product is deleted and success message "Product deleted" displays. Product removed from list. | Pass |  |  | High
|  | PROD_14 | Verify editing a product shows a success message and updates details in "Choose Product" list. | Product exists in "Choose Product". | 1. Click "Edit" on a product in the list. 2. Modify fields and save. | New Name: Chcolate Cake Updated Price = 410, New Price: 350 | Success message "Product updated successfully" displays. | Success message "Product updated successfully" displays. | Pass |  |  | High
|  | PROD_15 | Verify "radio button" functionality with ID column. | Verify clicking radio button opens a tab and shows correct data and clicking again close the tab. | 1. Click on "Products" in the sidebar. 2. Click radio "+" button with any product. | N/A | Description tab opens showing correct data and closes again when clicked. | Radio button works fine but description is wrong. Actual price and discounted price are same. | Fail
|  | PROD_16 | Verify toast messages display appropriately for adding, updating, and deleting products. | N/A | 1. Add, edit, or delete a product and observe toast messages. | N/A | Toast messages for each action appear in the lower right (e.g., "Product added", "Product updated"). | Toast messages "success" appears for each action on top of screen . | Pass |  |  | Low
PROD_SCEN_02 | Category page functionalities | PROD_CAT_01 | Verify that the "Add Category" button displays a popup for entering new category details. | On category page, user is logged in | 1. On the dashboard navbar, click on "Products". 2. Click on "Product Category". 3. Click on "Add Category". | N/A | A popup appears with fields to enter category details. | Popup appears with required fields. | Pass |  | - | High | No
|  | PROD_CAT_02 | Verify that adding a new category appears in the category list. | Category added successfully | 1. Add a new category. 2. Check if it appears in the category list. | Category: "New Category" | The new category appears in the category list. | Category is added and visible in the list. | Pass |  | - | High | No
|  | PROD_CAT_03 | Verify error handling for incorrect name when adding a new category of products. | User on "Add Category" popup | 1. Enter an invalid name (e.g., special characters) for the category. 2. Try saving the category. | Category: "@Category123" | An error message appears indicating invalid characters in the name. | No error message, category added. | Fail |  | Special characters allowed in category name. | High | No
|  | PROD_CAT_04 | Verify category name is unique and does not allow duplicates. | On "Add Category" page | 1. Add a category with an existing name. 2. Try saving the new category. | Category: "Existing Category" | An error message appears stating the category name already exists. | No error message, duplicate category added. | Fail |  | No validation for duplicate category names. | High | No
|  | PROD_CAT_05 | Verify adding/deleting a category shows a success toast message. | User is on category page | 1. Add a new category. 2. Delete the added category. 3. Check for a success toast message. | Category: "New Category" | Success toast message appears for both adding and deleting the category. | Success messages shown. | Pass |  | - | High | No
|  | PROD_CAT_06 | Verify the search bar on the page works fine for categories. | User on category page with multiple categories | 1. Enter a search term in the search bar. 2. Check if the category list filters accordingly. | Search Term: "Category" | The category list is filtered to show matching categories. | Categories are filtered as per search term. | Pass |  | - | Medium | No
|  | PROD_CAT_07 | Verify sorting arrows in each column work. | User on category page | 1. Sort categories by ID, name, and priority using the sorting arrows. 2. Check if columns are sorted correctly. | N/A | Categories are sorted correctly by ID, name, and priority, except for the status column. | Sorting works for ID, Name, and Priority. | Fail |  | Sorting issue with the status column. | Medium | No
|  | PROD_CAT_08 | Verify "Show Entries" button and "Next/Previous" pagination work as expected. | User on category page | 1. Click on the "Show Entries" dropdown and select different values. 2. Click on the pagination buttons. | Entries: 10, 20 | The category list updates to show the selected number of entries per page, and pagination works correctly. | Pagination works correctly. | Pass |  | - | Medium | No
|  | PROD_CAT_09 | Verify setting priority for a product from a dropdown in the priority column works fine, and checks for duplicates. | User on category page | 1. Set the priority for a product in the priority column. 2. Try setting a duplicate or existing priority. | Priority: "1", "0" | Priority should be updated for the product, and duplicates should be avoided. | Priority resets to "0" when set to existing value. | Fail |  | Priority reset issue when setting duplicate values. | High | No
|  | PROD_CAT_10 | Verify that the status for each category can be changed. | User on category page | 1. Change the status of a category from "On" to "Off" or vice versa. | Category: "Sample Category" | The status of the category should toggle successfully. | Status changes successfully. | Pass |  | - | Medium | No
|  | PROD_CAT_11 | Verify the "Edit Category" button shows a popup for editing and allows category name change. | Category exists in the list | 1. Click the "Edit" button next to a category. 2. Edit the category name in the popup. 3. Save the changes. | Category: "Old Category" | A popup appears with the category name pre-filled. After editing, the name should update in the list. | Category name is updated successfully. | Pass |  | - | High | No

## Reports
Scenario TID | Test Scenario | Test Case ID | Test Case Description | Preconditions | Test Data | Test Steps | Expected Result | Actual Result | Status | Executed QA Name | Misc (Comments) | Priority | Is Automated
Order_Report_SCEN_2 | Verify Delivery Time Report and other functionalities of order report module. | ORD-RP-01 | Verify if the report reflects the selected vendor's data. | User is logged in and has access to the Reports module. | 1. Navigate to Reports Management. 2. Select "Order Report". 3. Choose a specific vendor from the dropdown in the delivery time report. 4. View the report results. | Vendor: Specific Vendor | Delivery metrics should reflect the selected vendor's data accurately. | Delivery metrics showing incorrect data. | Fail |  | Issue with data display for selected vendor. | High | No
|  | ORD-RP-02 | Verify if the Order Report displays correct orders for the date range. | User is logged in and has access to the Reports module. | 1. Navigate to Reports Management. 2. Select "Order Report". 3. Set the date range to 01/01/2024 to 01/31/2024. 4. Select "Delivered" status. 5. View the report results. | Date Range: 01/01/2024 to 01/31/2024, Order Status: Delivered, Vendor: All Branches | Orders matching the selected criteria are displayed. | Orders matching the selected criteria displayed. | Pass |  | All criteria are met successfully. | High | No
|  | ORD-RP-03 | Verify if the Order Report reflects canceled orders accurately. | User is logged in and has access to the Reports module. | 1. Navigate to Reports Management. 2. Select "Order Report". 3. Set the date range to 01/01/2024 to 01/31/2024. 4. Set the order status to "Canceled". 5. Select a specific vendor. 6. View the results. | Date Range: 01/01/2024 to 01/31/2024, Order Status: Canceled, Vendor: Specific Vendor | Canceled orders for the selected vendor and date range should be accurately displayed. | Status Dropdown is not functioning as expected. | Fail |  | Status selection does not work. | High | No
|  | ORD-RP-04 | Verify if the order data table’s search functionality works. | On the Order Report page. | 1. Use the search functionality to search for a specific order ID (e.g., "Order123"). | Search term: "Order123" | The results should match the search term and display the corresponding order in the data table. | Works as expected and displays correct results. | Pass |  | Search works fine. | Medium | No
|  | ORD-RP-05 | Verify if the sorting functionality works in the order data table. | On the Order Report page. | 1. Use the sorting arrows in the columns (e.g., Order ID, Date) to sort by ascending or descending order. | N/A | The columns should be sorted correctly in ascending or descending order. | Sorting works as expected. | Pass |  | Sorting functionality is fine. | Medium | No
|  | ORD-RP-06 | Verify if the pagination buttons (Next/Back) work properly in the order report. | On the Order Report page. | 1. Click on the "Next" or "Back" pagination buttons to navigate through the pages. | N/A | The report pages should switch accordingly, showing the correct set of entries for the page. | Pagination works correctly. | Pass |  | Pagination is functional. | Medium | No
Rider_Report_Scen_2 | Verify rider report page functionlities and display of data. | RD-RP-001 | Verify if the Rider Report displays correct data for the selected rider. | User is logged in and has access to Reports module. | Date Range and time: 01/01/2024 to 01/31/2024, Selected Rider: John Doe | 1. Navigate to Reports Management. 2. Select "Rider Report." 3. Set date range, time and select rider. 4. View the report results. | Rider performance metrics are displayed accurately. | No data displayed | Fail |  |  | High

## 123
Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14
TC-UM-005 | Email: admin@example.com Password: validpassword | Verify appropriate message if there's no database access. | Simulate database disconnection. | 1. Navigate to the login page. 2. Enter valid credentials. 3. Click "Login." | Error message "Unable to connect to the database" is displayed. | Not Executed