## Sheet1
Bug Report Project Anaar
Bug ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Environment | Screenshots/Attachments | Status | Assigned To | Date Reported | Resolved Date | Comments
B-001 | New Rider function not working | When attempting to add a new rider, a success message appears, but the new rider is not displayed in the riders list. | 1. Go to the website. 2. Log in with admin credentials. 3. Navigate to the riders tab. 4. Click on rider info. 5. Click on the "Add Rider" button. 6. Fill in the necessary details. 7. Click on "Add." | New rider should be added and visible in the riders list. | A success message pops up, but the rider is not shown in the list. Logging in on the app shows the message "user is not a rider." | Major | High | Windows 10 and Android | No | Open | - | 2024-10-31 | - | -
B-002a | Long photo name issue | Photo name overflows the input box when it's too long. | 1. Go to the website. 2. Log in with admin credentials. 3. Navigate to the riders tab. 4. Click on rider info. 5. Click on the "Add Rider" button. 6. Fill in the necessary details, including a photo with a long name. | Photo name should remain within the prescribed box. | Long photo names go out of the box. | Minor | Medium | Windows 10 and Android | No | Open | - | 2024-10-31 | -
B-002b | Photo size limit issue | No limit on photo size when uploading a new rider photo. | 1. Go to the website. 2. Log in with admin credentials. 3. Navigate to the riders tab. 4. Click on rider info. 5. Click on the "Add Rider" button. 6. Upload a photo larger than the allowed size. | Should limit photo size; if exceeded, an error message should appear. | No validation for photo size; larger photos are accepted. | Major | High | Windows 10 and Android | No | Open | - | 2024-10-31 | -
B-002c | Phone number validation issue | The system does not require a valid phone number format when adding a new rider. | 1. Go to the website. 2. Log in with admin credentials. 3. Navigate to the riders tab. 4. Click on rider info. 5. Click on the "Add Rider" button. 6. Enter an invalid phone number. | A valid phone number should be required. | Invalid phone numbers are accepted without validation. | Major | High | Windows 10 and Android | No | Open | - | 2024-10-31 | -
B-002d | Password criteria issue | The system does not enforce password complexity requirements when adding a new rider. | 1. Go to the website. 2. Log in with admin credentials. 3. Navigate to the riders tab. 4. Click on rider info. 5. Click on the "Add Rider" button. 6. Fill in password without special characters or length restrictions. | Password should meet length and complexity requirements. | Passwords without restrictions are accepted. | Major | High | Windows 10 and Android | No | Open | - | 2024-10-31 | -
B-002e | Unreadable photo acceptance issue | The system accepts blurred or unreadable photos when adding a new rider. | 1. Go to the website. 2. Log in with admin credentials. 3. Navigate to the riders tab. 4. Click on rider info. 5. Click on the "Add Rider" button. 6. Upload a blurred or unreadable photo. | Only clear photos should be accepted. | Unreadable/blurred images are accepted without error. | Major | High | Windows 10 and Android | No | Open | - | 2024-10-31 | -